LIBERIA EXTRACTIVE INDUSTRIES TRANSPARENCY INITIATIVE (LEITI)

STATEMENT OF BUDGET Vs ACTUAL

| Objective 1 Contributing towards accurate domestic resource mobilization in support of the Government's ARREST Agenda for Prosperity and Development; |  |  |  |
| --- | --- | --- | --- |
| Activities | Output | Cost | Actual |
| Production of LEITI's 16th EITI Report in line with the 2023 EITI Standard | 15th and 16th EITI Reports are produced and printed | 120,000.00 | US$111,416.02 |
| Anti-Corruption, Energy Transition, Contract Transparency, Beneficial Ownership, Energy Transition, Mainstreaming, etc.. |  |  |  |

|  |  |  |  | Budget | Actual |
| --- | --- | --- | --- | --- | --- |
| Updating and dissemination of LEITI Simplified Contract Matrix | An updated, simplified contract matrix is developed and disseminated throughout the country. | LEITI Secretariat/ MSG | Jan- December 2025 | 60,0000.00 | US$54,348 |
| Conduct a post-award process audit on awarding Mining and Forestry Sectors licenses. | A post-award process audit report produced | LEITI Secretariat/ MSG | Jan- December 2025 | 40,000.00 | Not implemented |
| Conduct a risk assessment on the awarding of licenses in the mining sector | A risk assessment report is produced | LEITI Secretariat | December 2025 | 20,000.00 | Not implemented |
| Production of an Environmental Impact Report | A study report on the Social, Economic, and Environmental impact of small-scale mining, forestry, and agricultural activities is produced. | LEITI Secretariat | December 2025 | 25,000 | Not implemented |
| Development of a Mainstreaming Portal | LEITI Mainstreaming Portal is developed | LEITI Secretariat/MSG | December 2025 | 15,000.00 | Not implemented |
| Conduct a Scoping Assessment to determine the impact of the Government of Liberia's Policies related to Energy and the country's preparedness for the Energy Transition. | A Scoping Assessment Report is produced | LEITI Secretariat/MSG | December 2025 | 20,000.00 | Not implemented |
| Objective 3: Enhancing Timely Communication and Public Awareness for Effective EITI Implementation |  |  |  |  |  |
| Dissemination of the 13th, 14th , 15th and 16th Summary EITI Reports | Summary reports are produced and printed. | LEITI SEC/ MSG | December 2025 | 140,000.00 60,000.00 | US$180,510.00 |

| Produce sectorial reports, infographics, and other compelling visual aids to ensure the LEITI reports are presented more creatively and user-friendly to the public. | Sectorial reports and infographics are produced. | LEITI Secretariat/ MSG | December 2025 | 15,000.00 | US$15,000.00 |
| --- | --- | --- | --- | --- | --- |
| Production of a series of radio dramas, jingles, and short video skits using renowned comedians and other relevant individuals that will be played on various radio stations across the country | Dramas, Jingles, and short videos are produced and played on various radio stations throughout the country. | LEITI Secretariat/ MSG | December 2025 | 10,000.00 | Not implemented |
| Conduct dialogues between the Government and Companies, Companies and CSOs, CBOs and other relevant stakeholders, and between Government, CSOs, CBOs, and LEITI MSG Members. | Comprehensive dialogue reports are produced. | LEITI Secretariat/ MSG | December 2025 | 50,000.00 | Not implemented |
| Conduct two debates amongst high schools and universities, specifically around contract transparency and SDFs, and generally around issues affecting Natural Resource Governance. | Events reports are produced. | LEITI Secretariat/ MSG | December 2025 | 40,000.00 | Not implemented |
| Objective 4: Providing evidence-based information to the Executive and Legislative branches of Government for informed decision-making to ensure citizens benefit |  |  |  |  |  |
| Production of a Compliance Review Report of Concessionaries to ensure that they are meeting the Social- Corporate Responsibilities and dissemination | A Compliance Report is produced | LEITI Secretariat/ MSG | December 2025 | 60,000.00 | Ongoing |
| Production of a Compliance Report on the renewal processes of | A Compliance Report is produced | LEITI Secretariat/ MSG | December 2025 | 25,000.00 | Not implemented |

| various licenses in the Mining, Agriculture, and Forestry Sectors |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 5: Capacity building for effective EITI Implementation |  |  |  |  |  |  |  |  |
| Capacity building for journalists, women groups, CSOs, CBOs, youth and students, groups, and media institutions around effective dissemination of the EITI reports, investigation, verification, and reporting of BO information, etc. | Workshop report and attendance register are developed | LEITI MSG | Secretariat/ | December 2025 | 20,000.00 |  | Not implemented |  |
| Capacity building and consultative workshop with members of the Natural Resource Committees of the Senate and the House of Representatives to enhance accountability and transparency | Workshop report and attendance register are developed | LEITI MSG | Secretariat/ | December 2025 | 20,000.00 |  | Not implemented |  |
| Consultative workshop with Anti-Corruption institutions to enhance stakeholders' engagement and awareness | Workshop report and attendance register are developed | LEITI MSG | Secretariat/ | December 2025 | 20,000.00 |  | Not implemented |  |
| Capacity building for anti-corruption agencies to build understanding and use of BO data from the LBR | Workshop report and attendance register are developed | LEITI MSG | Secretariat/ | December 2025 | 20,000.00 |  | Not implemented |  |

| LEITI Secretariat Staff Salaries |  |  |  | December 2025 | 373,215.00 | US$373,215 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Stationery for Office use |  | LEITI | Secretariat | December 2025 | 24,000.00 | US$16,113 |  |
| Fuel & Lubricant- Generator |  | LEITI | Secretariat | December 2025 | 96,000.00 | US$56,530 |  |
| Regular Monthly Meeting Refreshments |  | LEITI | Secretariat | December 2025 | 14,400.00 | US$7,617.00 |  |
| Monthly Honorarium/Sitting - MSG Members, ($100/member) 12 months |  | LEITI | Secretariat | December 2025 | 41,000 | US$40,741.44 |  |
| TOTAL: |  |  |  | December 2025 |  |  |  |